## Sheet1
Activity / Stakeholders | Implementation Partner | Project Manager | Team Lead | Quality manager | Procurement Manager | HR | Software Engineer – Application – Tech. | System Engineer – Infrastructure | Software Engineer – HR / Payroll – Functional | Software Engineer – CRM – Functional | Software Engineer – email & tech support | System Engineer – Virtualization | System Engineer - Storage | Network Engineer | Data Base – Admin | System Admin | CIO
Initiating |  | R | R | [13 empty] | I
Requirement Gathering
Requirement gathering |  | R | A |  |  |  | R | R | R | R | R | R | R | R | R | R
Requirement Gathering Milestone |  | R | [14 empty] | I
Requirement Analysis
Conduct Planning Workshop |  | R | A |  |  |  | R | R | R | R | R | R | R | C | C | C
Requirement Analysis |  | R | R | I |  |  | C | C | C | C
Requirement Analysis Milestone |  | R | [14 empty] | I
Planning
Define Scope
Define Scope |  | R | R
Scope Definition Milestone |  | R
Develop Project Schedule
Build Work Breakdown Structure |  | R | R | C
Develop Resource Plans |  | R | R
Develop Risk Plans
Identify Risks |  | R | R | C |  |  | C | C | C | C | C | C
Analyze Risks |  | R | R | C
Document Risk Management Plans |  | R | R | C
Plan for Quality
Document Quality Management Plan |  | R | A | C
Organize Project Resources
Develop Organization Structure |  | R | A | C
Develop Staffing Plan |  | R | A | C | C | C
Develop Procurement Plans
Determine Procurement Requirements |  | R | A |  | R
Define Subcontractor Scope |  | R | A | C | C | C | C | C | C
Identify Potential Subcontractors |  | R | R |  | R
Document Subcontractor Management Plan |  | R | A |  | R
Develop Financial Plan
Prepare Financial Plan |  | R | A | A | A
Develop Project Support Plans
Document Communications Management Plan |  | R | A
Develop Project Management Plan
Document Project Management Plan |  | R | A
Scope, Partner, BOQ finalization and ordering
Scope Finalization
Architecture Signoff |  | R | A | C |  |  | C | C | C | C | C | C
Design Sign-off |  | R | A | C |  |  | C | C | C | C | C | C
Architecture and Design Sign off |  | R | A | C |  |  | C | C | C | C | C | C
Hardware BOQ Preparation |  | R | A | C |  |  | C | C | C | C | C | C
Software BOQ Preparation |  | R | A | C |  |  | C | C | C | C | C | C
Manage Project Communication
Review Progress |  | R | A | A | A | [11 empty] | I
Implementation partner Finalization
Issue Requisition Documents |  | I | A | C | R
Partner Identification Milestone |  | I | A | C | R
Evaluate Responses |  | R | R | C | R
Negotiate Partner Scope of Work | I | R | A | I | R | I | [10 empty] | I
Implementation Scope Sign off with the partner | C | R | A | I | R | I | [10 empty] | I
H/W BOQ Finalization with partner | A | R | A |  |  |  |  | C
S/W BOQ Finalization with partner | A | R | A |  |  |  | C
H/W BOQ Order | I | I | I | I | RA |  | C | C
S/W BOQ order | I | I | I | I | RA |  | C | C
H/W & S/W Order Milestone |  | R |  |  | A | [11 empty] | I
H/W , S/W delivery, Implementation, Migration
Hardware & Software Delivery
H/W delivery | I | I | R | I | I |  | I | I
S/W Delivery | I | I | R | I | I |  | I | I
H/W & S/W Delivery Milestone |  | R | [14 empty] | I
H/W & S/W audit and confirmation | C | R | A | R | R |  | C | C
Implementation
Start Implementation by Partner | R | A | A | C |  |  | C | C
Hardware installation | R | A | A | C |  |  |  | C
Software installation | R | A | A | C |  |  | C
System configuration | R | A | A | C |  |  |  | C | C | C | C | C | C | C | C | C
System Testing and audit | R | A | A | C |  |  |  | C | C | C | C | C | C | C | C | C
Data Migration Design | R | A | A | C |  |  | C | C
Migration Build | R | A | A | C |  |  | I | I
Data Validation and Execution | R | A | A | C |  |  | C | C
Data Transition | R | A | A | C |  |  | I | I
Perform Quality Control
Testing post Migration | R | A | A | C |  |  | A | A | I | I | I | I | I | I | I | I
UAT & Feedback | R | A | A | C |  |  | A | A | A | A | A | A | A | A | A | A
Monitoring and Control
Monitoring and reporting |  | R | R | R | [12 empty] | I
Project Go live Milestone |  | R | R | R | [12 empty] | I
Go Live
Handover & Training
Handover | R | R | R | I
Training | R | R | R | I
Project Handover Milestone | R | R | [14 empty] | I
Partner Project Signoff
Assess Satisfaction |  | R | A | I | I
Summarize Project Results and Lessons Learned |  | R | A | I | I
Review and Recognize Team Performance |  | R | A | I | I
Close Out the Project Records |  | R | A
Documentation |  | R | A
Project Closer Signoff | R | R | A | R | R | [11 empty] | I
Project Closure
Project & Contract closure and final signoff |  | R |  | R | R | [11 empty] | R
Project close